## data
Task_ID | Assigner | Next Sprint? | Completed | Date | Completion Date | Nature | Roadblock | Task_Description | tASK_PRIORITY | Hours | Task_workload FTE | Closing Comment (If Applicable)
1 | Brian | N | Y | 2021-06-07 | 2021-06-09 | Onboarding | None | get VPN access sorted | 4 | 0.5 | 0.064516
2 | Brian | N | Y | 2021-06-07 | 2021-06-09 | Onboarding | None | Read Teams documentation and familiarize with file locations | 4 | 2 | 0.25806
3 | Brian | N | Y | 2021-06-07 | 2021-06-09 | Onboarding | None | Setup SQL Task Tracker | 4 | 2 | 0.25806
4 | HR | N | Y | 2021-06-07 | 2021-07-30 | Onboarding |  | Get through Eloomi onboarding modules | 3 | 50 | 6.4516 | N/A
5 | Simon | N | Y | 2021-06-07 | 2021-07-21 | Streamline/Improvements | None | Streamlining Datasources and interrogate PowerBI accuratcy(Contracts tab) | 1 | 20 | 2.5806 | Happy with All except savings bar. New Task to rebuild Savings data source
6 | Simon | N | Y | 2021-06-07 | 2021-06-09 | Onboarding | None | Understand Savings report) | 3 | 6 | 0.77419
7 | Simon | N | Y | 2021-06-07 | 2021-06-09 | Onboarding | None | Reach to Will foley(IT) to get access to SAP | 4 | 1 | 0.12903
8 | Simon | N | Y | 2021-06-07 | 2021-06-09 | Onboarding | None | get Pbix file off Dan Craley | 4 | 1 | 0.12903
10 | Simon | N | Y | 2021-06-07 | 2021-06-09 | Onboarding | None | Familiarize myself with intranet procurement sharepoint | 4 | 1 | 0.12903
11 | Simon | N | Y | 2021-06-07 | 2021-06-09 | Ad-hoc | None | Troubleshooting global dashboard why datas not putting through | 4 | 2 | 0.25806
14 | Brian | N | Y | 2021-06-08 | 2021-07-30 | Onboarding | None | competent with wednesday meeting schedule | 2 | 4 | 0.51613 | N/A
16 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | update on when the KPI rport will be available | 2 | 0.5 | 0.064516
17 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | Setup for team site with security control for sensitive client information | 4 | 1 | 0.12903
18 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | SRM page report p.42 of instruction, are we suppose to build it, are you running it? activity tracker not working, needs conversation Nick | 4 | 1 | 0.12903
19 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Onboarding | None | Learn to Navigate teams | 4 | 2 | 0.25806
20 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Onboarding | None | Read through 50 page instruction on how to run the pbix file and maintain datasources | 4 | 3 | 0.3871
21 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Onboarding | None | Setup sap hana account | 4 | 2 | 0.25806
22 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | Conversation with Simon rolling 12 not rolling, dont know where the source is actaully from | 4 | 1 | 0.12903
23 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | GNFR Procrement overview tab need MAYs data | 4 | 1.5 | 0.19355
24 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | 1 VENDOR MIDDLESOFT missing in masterdata sheet, vendor code 23027.vendor masterdatasheet is in the BI reporting file | 4 | 0.5 | 0.064516
25 | Brian | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | troubleshoot usual spend 260m, 199 logging for overall across all category of spend, data accuracy needs improvement | 4 | 2 | 0.25806
26 | Dan | N | Y | 2021-06-08 | 2021-06-10 | Onboarding | None | read GNFR Cleared Spend Report guide | 4 | 1 | 0.12903
27 | Nick | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | Fix SRM middle chart over 100k | 3 | 1 | 0.12903
28 | Nick | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | SRM data is from kpi report, make the top chart work | 3 | 1 | 0.12903
29 | Nick | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | SRM Tab understanding, | 4 | 0.5 | 0.064516
30 | Nick | N | Y | 2021-06-08 | 2021-06-10 | Onboarding | None | Read Ryan handover guide | 4 | 2 | 0.25806
31 | Nick | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | learn/ ask rebecca case on how to maintaining mailbox | 4 | 2 | 0.25806
32 | Siobhan | N | Y | 2021-06-08 | 2021-07-05 | Ad-hoc | None | Contract coverage report Region can be more pinpoint, currently reporting bysupplier location, ideally where its funded. | 4 | 4 | 0.51613 | Raw Spend collated into distince vendor number, (If further details wanted can expand heirachy
33 | Siobhan | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | Quick Win double ribbon, breakdown on region as well as category of spend | 4 | 1 | 0.12903
34 | Siobhan | N | Y | 2021-06-08 | 2021-06-10 | Ad-hoc | None | Top ribbon on primary classification not toggling | 4 | 0.5 | 0.064516
35 | Dan | N | Y | 2021-06-09 | 2021-07-07 | Ad-hoc | None | Reverse Engineer kpi live datasources and map out | 1 | 35 | 4.5161 | Task Obsolete, whole report rebuilt
36 | Dan | N | Y | 2021-06-09 | 2021-06-11 | Ad-hoc | None | docusign access for Ali | 4 | 0.25 | 0.032258
37 | Dan | N | Y | 2021-06-09 | 2021-06-11 | Ad-hoc | None | Reverse engineer contract coverage report datasources and mapout | 4 | 5 | 0.64516
38 | Perrin | N | Y | 2021-06-09 | 2021-06-11 | Ad-hoc | None | Group Buyer PowerPoint for Perrin | 4 | 0.5 | 0.064516
39 | Brian | N | Y | 2021-06-10 | 2021-06-12 | Ad-hoc | None | Quick Excel Analysis on Stores and management fees from HR | 4 | 0.5 | 0.064516
146 |  | N | Y | 2021-09-01 | 2021-09-03 | Ad-hoc |  | load in august mentor data/saving
41 | Brian | N | Y | 2021-06-14 | 2021-06-16 | Ad-hoc | None | Lisa Baker docusign access | 4 | 0.25 | 0.032258
42 | Brian | N | Y | 2021-06-14 | 2021-06-16 | Onboarding | None | Winshuttle Access From Phil Humpries | 4 | 1 | 0.12903
43 | Brian | N | Y | 2021-06-14 | 2021-06-16 | Onboarding | None | Intranet edit Access From Kevin Hawkes | 4 | 1 | 0.12903
44 | Simon | N | Y | 2021-06-14 | 2021-07-08 | Ad-hoc | None | Update Intranet Procurement team Org Chart. | 4 | 4 | 0.51613 | N/A
45 | Brian | N | N | 2021-06-15 | Not applicable | Regular reporting | None | Monthly for all of my workstreams, map out steps on visio | 4 | 1 | 0.12903 | N/A
46 | Brian | N | Y | 2021-06-15 | 2021-06-17 | Ad-hoc | None | SAP video not helpful with setup, look for support from IT | 4 | 2 | 0.25806
47 | Brian | N | N | 2021-06-15 | Not applicable | Regular reporting | None | Document Ongoing workstream and procedures | 4 | 0.5 | 0.064516 | N/A
48 | HR | N | Y | 2021-06-15 | 2021-06-17 | Ad-hoc | None | Paul Wilson Docusign Access | 4 | 0.25 | 0.032258
49 | Simon | N | Y | 2021-06-15 | 2021-06-17 | Onboarding | None | Quick Datasheet manipulation | 4 | 1 | 0.12903
51 | Simon | N | Y | 2021-06-15 | 2021-06-17 | Ad-hoc | None | SAP Training | 4 | 3 | 0.3871
52 | Simon | N | Y | 2021-06-15 | 2021-06-17 | Ad-hoc | None | Download SAP Tutorial video and reupload in centralized team space | 5 | 1 | 0.12903
53 | Brian | N | Y | 2021-06-18 | 2021-07-16 | Onboarding | None | Ask Dan for a list of Acronyms for SAP hana studio Classification tables | 1 | 0.5 | 0.064516 | N/A
54 | Brian | N | Y | 2021-06-18 | 2021-07-21 | Onboarding | None | Clarify maintanence task on handout guide, specifically for winshuttle workstream | 4 | 0.5 | 0.064516 | No one Knows, self discovery and handout guides took a while
55 | Perrin | N | N | 2021-06-18 | Not applicable | Regular reporting | None | Maintain daily reporting on SAP PO updates for Sally Ponting | 4 | 0.25 | 0.032258
56 | Brian | N | Y | 2021-06-21 | 2021-07-21 | Ad-hoc | None | Personal BI Tracker, I want Comparism metrics sorted by today, with task nature category breakdown loaded in | 5 | 3 | 0.3871 | Happy with Metrics
57 | Brian | N | Y | 2021-06-21 | 2021-06-23 | Onboarding | None | Understand more about who owns global activity tracker. potential for process improvement | 3 | 0.25 | 0.032258
58 | Nick | N | Y | 2021-06-21 | 2021-06-22 | Ad-hoc | None | kpi_live: Fix Data errors in SRM Tab | 3 | 3.5 | 0.45161 | N/A
59 | Simon | N | Y | 2021-06-21 | 2021-06-23 | Ad-hoc | None | double check contract coverage report auto-refresh switched on 6pm tuesday | 1 | 0.5 | 0.064516 | Checked Dataflow autorefreshs
60 | Simon | N | Y | 2021-06-21 | 2021-06-23 | Ad-hoc | None | Contract Coverage report donut chart set colour change green-amber at 95% threshold | 4 | 0.5 | 0.064516
61 | Brian | N | Y | 2021-06-22 | 2021-06-24 | Ad-hoc | None | Amend Personal tracker report, add time consumption field of task, and task priority on dashboard | 5 | 0.5 | 0.064516 | Counted in hours, direct conversion to FTE (Full time day equivalents)
65 | Brian | N | N | 2021-06-22 | Not applicable | Regular reporting | None | Raise Question with Docusign Janet monthly on licensing and the quantity of of envs we have with deleting onboarding/offboarded colleages. | 3 | 1 | 0.12903 | Ongoing Maintanence, wont Close
66 | Brian | N | Y | 2021-06-22 | 2021-06-24 | Ad-hoc | None | Ongoing reporting tasks have regular time blocked out on outlook Calender | 4 | 0.25 | 0.032258
67 | Brian | N | Y | 2021-06-22 | 2021-06-24 | Ad-hoc | None | Ask Ewan about End-to-End Windshuttle Process and document current failing Points | 4 | 2.5 | 0.32258
68 | Brian | N | Y | 2021-06-22 | 2021-06-24 | Ad-hoc | None | Personal Tracker--- create relative workload field, task nature and priority field | 4 | 4 | 0.51613
69 | HR | N | Y | 2021-06-22 | 2021-06-24 | Ad-hoc | None | Revoke Amy Marino Docusign | 4 | 0.25 | 0.032258
70 | Katy | N | Y | 2021-06-22 | 2021-06-24 | Ad-hoc | None | Supply Chain Cost to Serve PO Extract from SAP, for Katy +Perrin | 1 | 1 | 0.12903
71 | Simon | N | N | 2021-06-22 | Not applicable | Regular reporting | None | Thursday 1430 Docusign Check for pending access requests | 3 | 0.5 | 0.064516 | Ongoing Maintanence, wont Close
72 | Simon | N | N | 2021-06-22 | Not applicable | Regular reporting | None | Mid week, EOW Procurement Mailbox Check | 4 | 0.5 | 0.064516 | Ongoing Maintanence, wont Close
73 | Simon | N | Y | 2021-06-22 | 2021-06-24 | Onboarding | None | Gain Acccess to Concur | 2 | 0.01 | 0.0012903
75 | Simon | N | Y | 2021-06-22 | 2021-07-21 | Ad-hoc | None | Draw up Windshuttle end-to-end responsibility and hyperlink to responsibility one-pager | 2 | 3.5 | 0.45161 | Scheduled in 2 hours with Anna baker to learn this
76 | Simon | N | Y | 2021-06-22 | 2021-06-24 | Ad-hoc | None | Make changes to SEA Owner on Windshuttle | 4 | 1 | 0.12903
77 | Katy | N | Y | 2021-06-23 | 2021-06-25 | Ad-hoc | None | Export SAP Data for Royal Mail, Compare Blanket spend and try to find actual spend through invoice | 1 | 0.5 | 0.064516
78 | Perrin | N | Y | 2021-06-23 | 2021-06-25 | Ad-hoc | None | Winshuttle teams instruction need validation with CDS Phil Humphry, Kevin Hawk as it needs to go Live ASAP | 1 | 3 | 0.3871
79 | Perrin | N | Y | 2021-06-23 | 2021-06-25 | Ad-hoc | None | Contract Coverage report Change dropdown menu back to Click buttons, more user friendly | 1 | 0.5 | 0.064516
80 | Simon | N | Y | 2021-06-23 | 2021-06-25 | Ad-hoc | None | Contract Coverage report is showing No Contract required, but also showing up in expiring next 6months, set exclusion rule | 1 | 2 | 0.25806
81 | Simon | N | Y | 2021-06-23 | 2021-06-25 | Ad-hoc | None | Contract Coverage report Refresh report and set autorefresh to tuesday 6pm, Siobhan corporate entry NEEDS to come off | 1 | 2 | 0.25806
82 | Simon | N | N | 2021-06-23 | Not applicable | Regular reporting | None | Weekly Teams Page Clean up | 3 | 0.5 | 0.064516 | N/A
83 | Siobhan | N | Y | 2021-06-23 | 2021-06-25 | Ad-hoc | None | 2 clients vendor number 22987,11441 shouldnt pop up at all in Siobhans report | 1 | 0.5 | 0.064516
84 | Siobhan | N | Y | 2021-06-23 | 2021-06-25 | Ad-hoc | None | Consolidate 2 clients both with vendor number 22847 | 1 | 0.5 | 0.064516
85 | Siobhan | N | Y | 2021-06-23 | 2021-06-25 | Ad-hoc | None | HR data extract Request to include 2019 data (One-off) | 4 | 0.5 | 0.064516
86 | Perrin | N | N | 2021-06-28 | Not applicable | Regular reporting | On Hold, re-org in process, not sure who's going to own process | Deliver Windshuttle training monthly, 3 sessions across the week | 1 | 4 | 0.51613 | N/A
87 | Perrin | N | N | 2021-06-28 | Not applicable | Regular reporting | None | Maintain Global supplier and Buyer Distribution list weekly (Friday) for Sally Ponting | 3 | 0.25 | 0.032258 | N/A
88 | Perrin | N | N | 2021-06-28 | Not applicable | Regular reporting | None | Maintain daily marketing marketing PO updates for Sally Ponting | 3 | 0.25 | 0.032258 | N/A
89 | Brian | N | Y | 2021-07-06 | 2021-07-07 | Ad-hoc | None | Procurement Overview Page over80% contributing 20% chart needs fixin | 1 | 2 | 0.25806 | Fixed, Chart Conditional formating and % moving
90 | Brian | N | Y | 2021-07-07 | 2021-07-08 | Ad-hoc | None | Help Katy With fixing Global activity tracker entries | 2 | 0.5 | 0.064516 | N/A
91 | Brian | N | Y | 2021-07-07 | 2021-08-09 | Ad-hoc | broke links, people used to where things are, don’t move around until more fresh blood | try and move static files (Global activity tracker, mentor FY2021 Spend to shared teams folders and off sharedrive.) | 3 | 0.5 | 0.064516 | N/A
93 | Rebecca | N | Y | 2021-06-28 | 2021-06-29 | Ad-hoc | None | 27769 needs to come off rebecca's pile | 2 | 0.2 | 0.025806
94 | Siobhan | N | Y | 2021-06-28 | 2021-06-29 | Ad-hoc | None | 26793 needs to come off siobhans pile | 2 | 0.2 | 0.025806
95 | Perrin | N | Y | 2021-06-28 | 2021-07-16 | Streamline/Improvements | Discussion to be had across team | Line by Line Wednesday show potentially just go high level metrics, 1once a month line by line deepdive | 2 | 5 | 0.64516 | Conclusion reached, go through weekly trend. And deepdive into number metrics monthly
96 | Brian | N | Y | 2021-07-08 | 2021-07-21 | Ad-hoc |  | Learn how to check Payment terms (Get XK03 Access) | 2 | 2 | 0.25806 | Not suppose to have XK_03 Access. Forward enquiries to AP.
97 | Simon | N | Y | 2021-07-08 | 2021-07-13 | Ad-hoc |  | Reach out to Anne Baker to do Windshuttle form raising run through | 1 | 1.5 | 0.19355 | Ad -hoc help with actually filing the form required.
98 | Siobhan | N | Y | 2021-07-08 |  | Ad-hoc |  | ad hoc PO request for Siobhan (Italian tax) | 1 | 0.5 | 0.064516
99 | Simon | N | Y | 2021-07-08 | 2021-07-14 | Ad-hoc |  | upload windshuttle instructions from Simon to Purchase to Pay excellence centre, & Procurement team training | 1 | 0.2 | 0.025806
100 | Simon | N | Y | 2021-07-08 | 2021-08-11 | Ad-hoc |  | Data Clean for Global Activity Tracker, Fix Validation Columns | 1 | 2 | 0.25806 | End up rebuilding it from scratch. Too messy initially anyway
101 | Simon | N | N | 2021-07-08 | Not applicable | Regular reporting |  | Every Wednesday take snapshop of kpi live (Spend Under contract, no. of supplier under contract, YTD Average payment days vs LY, % of Supplier Spend over 80% | 1 | 0.5 | 0.064516
102 | Brian | N | Y | 2021-07-08 | 2021-08-09 | ad-hoc | Dataflows broke after takeover, manaully refreshing at the moment | Take over Dataflow on workspace, troubleshoot session with Dan scheduled to fix authentication credentials | 3 | 2 | 0.25806
110 | Rebecca | N | Y | 2021-07-09 |  | ad-hoc |  | Louide Contract not required | 1 | 0.1 | 0.012903
104 | Brian | N | Y | 2021-07-09 | 2021-07-15 | ad-hoc |  | draw up teams page structure visio | 2 | 2 | 0.25806
105 | Brian | N | Y | 2021-07-13 |  | ad-hoc | Awaiting final confirmation on what fields to keep on central view, then can go ahead and patch onto kpi live | Rebuild Global activity Tracker Offline | 1 | 20 | 2.5806
|  |  | Y | 2021-07-13 | 2021-07-14 | ad-hoc |  | SRM page deepdive, what the metrics mean, how should we change them | 1 | 1 | 0.12903
|  |  | Y | 2021-07-13 | 2021-07-14 | ad-hoc |  | Add PowerBI App tab onto general teams Page | 1 | 0.5 | 0.064516
107 | Brian | N | Y | 2021-07-13 | 2021-07-14 | ad-hoc |  | Check with Ewan that Nick Hill's Ven003 is reassigned to Rebecca. No confirmation today | 1 | 0.5 | 0.064516
108 | Simon | N | Y | 2021-07-14 | 2021-07-15 | Ad-hoc |  | Consolidate excel sheet understanding received from Simon into Filing structure on Teams. | 2 | 2 | 0.25806
109 | Phil | N | Y | 2021-07-14 | 2021-07-14 | Ad-hoc |  | Jade and Dr Peng mark off on contract not required List | 1 | 0.2
111 | Brian | N | Y | 2021-07-14 | Not applicable | ad-hoc |  | Consolidate global buyer supplier mailing list with existing live sheet from sally ponting | 1 | 0.5 | 0.064516
112 | Brian | N | Y | 2021-07-14 | 2021-08-09 | Ad-hoc | in Conversation with Dan on how to either rebuild, or use all of them throuh SAP connections | fix market dojo dataflow not working | 1 | 2 | 0.25806
40 | Brian | N | N | 2021-06-14 |  | Ad-hoc | Not Figured out Regular reporting pattern yet, org change | Data Producement Analtst Monthly Schedule on a timeline | 4 | 3 | 0.3871 | N/A
114 | Siobhan | N | Y | 2021-07-16 | 2021-07-20 | Ad-hoc |  | Fix New Supplier Pack hyperlink | 1 | 0.5 | 0.064516
115 | Brian | Y | Y | 2021-07-16 | 2021-07-30 | Ad-hoc |  | Sprint Model for personal tracker | 2 | 0.5 | 0.064516
114 | Siobhan | N | Y | 2021-07-23 | 2021-08-02 | Ad-hoc | Contract refresh Issues on Market Dojo, Dataflow broke, credential issue.. | OMD renewed, infospring on contract not required, figure out why they arent coming off the list. | 2 | 1 | 0.12903
115 | siobhan | N | N | 2021-07-26 | Not applicable | Regular reporting | Contract refresh Issues on Market Dojo, not validating "contract not required list as refresh cant pull through yet" | monthly spend report for each category of spend | 2 | 0.5 | 0.064516
116 | Perrin | N | Y | 2021-07-26 | 2021-08-18 | Ad-hoc |  | change metrics from 100K limit to 50 K Limit | 1 | 2 | 0.25806 | Phil too busy Ewan amended and closed ticket
117 | Perrin | N | Y | 2021-07-26 | 2021-08-18 | Ad-hoc |  | GNFR vendor form on winshuttle needs amending, 100k to 50k | 2 | 0.25 | 0.032258 | Phil too busy Ewan amended and closed ticket
118 | Perrin | N | Y | 2021-07-26 | 2021-08-11 | Ad-hoc | List sent off to CDS, awaiting response | GNFR vendor form, refresh dropdowns, some names are too old | 3 | 0.25 | 0.032258
119 | Brian | N | Y | 2021-07-26 |  | Ad-hoc | will break the report temporarily, should probably do out of hours | Change input method from marketDojo From dataflow to direct import | 3 | 1 | 0.12903
120 | Perrin | N | Y | 2021-07-26 |  | ad-hoc | need contextual understanding on each and every category and dry runthroughs | Learn every winshuttle dropdown meeting and hold monthly global training | 1 | 2 | 0.25806
113 | Brian | N | N | 2021-07-16 |  |  |  | build a list of SAP hahna acronyms for databases | 3 | 6 | 0.77419
122 | Simon | N | N | 2021-08-03 |  | Regular reporting |  | sending out regular reminders for monthly update on global actvity tracker End of Month | 1 | 0.1 | 0.012903
123 | Simon | N | Y | 2021-08-03 | 2021-08-13 | Ad-hoc |  | Amend colums on vendor master report | 2 | 0.1 | 0.012903
124 | Simon | N | Y | 2021-08-03 |  | ad-hoc |  | activate docusign account for Simon Jones | 2 | 0.15
124 | Simon | N | N | 2021-08-03 |  | Regular reporting |  | monthly Savings refresh from global activity tracker to Savings Tracker | 1 | 0.2 | 0.025806
125 | Simon | N | Y | 2021-08-04 | 2021-08-04 | ad-hoc |  | Agile 2.0 Tracker quick insight | 2 | 0.5 | 0.064516
125 | Simon | N | Y | 2021-08-04 | 2021-08-05 | ad-hoc | Siobhans out, no one else has super-admin, Raised with Account Lead, should be rsolved, need confirmation | get Simon elevated Market Dojo Access |  |  | 0
126 | Simon | N | Y | 2021-08-04 | 2021-08-19 | Ad-hoc | CDS dropdowns fixef, ALC team needs nudge/escalate to make website changes | get CDS to amend Winshuttle form | 1 | 1 | 0.12903
127 | Katy | n | N | 2021-08-06 |  | Regular reporting |  | Supplier roadmap report for Katy | 1 | 0.5 | 0.064516
128 | Simon | N | Y | 2021-08-10 | 2021-08-13 | Ad-hoc |  | Global activity tracker VBA amendment, Auto generate unique ID | 1 | 0.5 | 0.064516
129 | Simon | n | N | 2021-08-10 |  | Regular reporting |  | Global Activity tracker increase in scope, include category divided roadmap | 1 | 7 | 0.90323
130 | Simon | N | Y | 2021-08-10 | 2021-08-13 | Ad-hoc |  | Kpi Live, fix contract coverage donut, broke again after marketdojo api integrated | 1 | 1 | 0.12903 | Filters were limiting wrong metrics, chart seperated and fixed with individual parameters
131 | Simon | N | Y | 2021-08-10 | 2021-08-13 | Ad-hoc |  | kpi live pull in value column for contract gaps, and contract expiring in 6 months | 1 | 1.5 | 0.19355
132 | Simon | N | Y | 2021-08-11 | 2021-08-13 | Ad-hoc |  | investigate why some of the marketdojo contracts have left | 1 | 2 | 0.25806 | BD on the marketdojo side messed up, nothing to do with my tracker
121 | Brian | N | N | 2021-08-02 |  | Ad-hoc |  | fb1l dataflow not working, interrogate script in Ryans library and rebuild in power query | 2 | 3 | 0.3871
| Siobhan | N | Y | 2021-08-13 | 2021-08-13 | Ad-hoc |  | Fix ACH Agreement form | 1 | 1
128 | Hans | N | Y | 2021-08-16 | 2021-08-17 | Ad-hoc |  | Hans access to marketdojo, winshuttle, procurement mailbox, mailing list | 1 | 1.5 | 0.19355
128 | Simon | N | Y | 2021-08-11 | 2021-08-22 | Ad-hoc |  | Call helpdesk to figure out why my Teams Sync isnt working… bring up global activity tracker example
127 | Simon | N | N | 2021-08-11 |  | Ad-hoc | Support from Dan to familiarize myself with SQLhana | Write SQL Query in Hana to pull out monthly spend data per category | 1 | 6 | 0.77419
129 | Simon | N | Y | 2021-08-23 | 2021-08-29 | Ad-hoc |  | Change on AT tracker, Modify Titles, Fix VBA script for insert line button | 2 | 0.5 | 0.064516
130 | Simon | N | Y | 2021-08-23 | 2021-08-25 | Ad-hoc |  | freeze panes on AT tracker. | 2 | 1 | 0.12903
| Simon | N | Y | 2021-08-24 | 2021-08-24 | Ad-hoc |  | Handover extract for Siobhan
| Brian | N | Y | 2021-08-24 | 2021-08-24 | Ad-hoc |  | Replace Savings bar with new global activity tracker data
| Brian | N | Y | 2021-08-24 | 2021-08-25 | Ad-hoc |  | replace SRM tab with new global activity tracker data
133 | Simon | N | Y | 2021-08-25 | 2021-08-25 | Ad-hoc |  | re-assign katy's docusign envelopes to Hans and Simon
134 | Olivia | N | Y | 2021-08-25 | 2021-08-25 | Ad-hoc |  | Validate Imperial dade information
131 | Simon | N | Y | 2021-08-23 | 2021-08-29 | Ad-hoc |  | get overview savings targets filtering with the ITY |  |  | 0
135 | Siobhan | N | Y | 2021-08-25 | 2021-09-02 | Ad-hoc |  | Interrogate cateogry 3 fields on kpi misalignment |  |  | 0
|  | N | Y | 2021-08-25 | 2021-08-25 | Ad-hoc |  | Siobhan envoloop access for simon
136 | Simon | N | Y | 2021-08-25 | 2021-08-29 | Ad-hoc |  | interrogate top line metrics validation with Simon on the procuremet overview |  |  | 0
138 |  | N | Y | 2021-08-27 |  | Ad-hoc | N | Ali access to marketdojo, winshuttle |  |  | 0
139 | Simon | N | Y | 2021-08-27 | 2021-09-10 | Ad-hoc |  | central view tab comments data quality issue | 1 | 6 | 0.77419
140 | Simon | N | N | 2021-08-27 |  | Ad-hoc |  | SRM tab % bukd new calculated metric | 2 | 1 | 0.12903
141 |  | N | Y | 2021-08-27 | 2021-08-29 | Ad-hoc |  | YTD supplier setup time, validate with Simons output sheet |  |  | 0
142 |  | n | Y | 2021-08-29 | 2021-08-29 | Ad-hoc |  | docusign access for rebecca, andrea
143 |  | n | Y | 2021-08-29 | 2021-09-02 | Ad-hoc |  | Move all recorded training material to teams, create training calender
| Simon | N | N |  |  |  |  | fix/change overview metric on BI report |  |  | 0
142 | Simon | N | Y | 2021-09-13 | 2021-09-13 | Ad-hoc |  | Fault find on global activity tracker what loose links are causing error msg | 1 | 0.5 | 0.064516 | There were pathways pointing towards old excel files that were sitting on prem, These files have been moved but pathways remain. I have extracted data from old files into new tracker, but hyperlinks still active. Edited startup prompt to neglect errors
143 | Simon | N | y | 2021-09-13 | 2021-09-13 | Ad-hoc | need to alert team on owner vs procurmenet manager | Transfer contracts from Siobhan to Ali, Deactivate Siobhans acct | 1 | 0.5 | 0.064516
144 | Myself | N | Y | 2021-09-17 | 2021-09-20 | Ad-hoc |  | Building category of spend heirachy and reclassify for cleaner data | 2 | 0.5 | 0.064516
145 | Simon | N | Y | 2021-09-14 | 2021-09-14 | Ad-hoc |  | Pull through VDM data from PowerBI into SRM tab (ITY savings, and Rolling 12 ) | 2 | 0.25
146 | Simon | N | Y | 2021-09-14 | 2021-09-16 | Ad-hoc |  | Winshuttle Portal Update, Remove Procurement site specific Buyer list, Streamline and point at finance's central buyer supplier matric | 1 | 0.5 | 0.064516
147 | Simon | N | N |  |  | Ad-hoc |  | have the 2020 Data extracted from old tracker to add to current tracker to drive category breakdown of previos savings | 3 | 3 | 0.3871
148 | Simon | N | Y | 2021-09-16 |  | Ad-hoc |  | SRM data clean (Line by Line Validation) | 1 | 2 | 0.25806
148 | Simon | N | N | 2021-09-16 | 2021-09-16 | Ad-hoc |  | SRM metric change | 1 | 1
49 | Simon | n | Y | 2021-09-16 | 2021-09-16 | Ad-hoc |  | update intranet site
150 | Simon | n | n |  |  | Ad-hoc |  | ALC ven report cleanup
151 | Simon | n | Y | 2021-09-24 | 2021-09-24 | Ad-hoc |  | monthly winshuttle repoer included into powerBI
152 | Simon | n | Y | 2021-09-22 | 2021-09-23 | Ad-hoc |  | Draw out Data structure for kpi live | 2 | 2
153 | Simon | n | N |  |  | Ad-hoc |  | Rewrite Handover Guide | 1 | 8
154 | Simon | N | N | 2021-09-24 |  | Regular reporting |  | monthly update on winshuttle report in powerBI
| Simon |  |  |  |  | Ad-hoc |  | work with Lewis to add Primary category in market dojo
| Simon |  |  |  |  | Ad-hoc |  | Map out eccomerce, digital marketing on market dojo, re-assign after discussion with Ali and Simon and reach to Lewis to re-categorize on dojo end
| Simon |  | y | 2021-09-24 | 2021-09-24 | Ad-hoc |  | give Simon access to all categories on Dojo
Give Simon Super Admin to winshuttle , and market Dojo
Handover existing data reltaed tasks to Dan C
Handover existing Team support Tasks to Simon

## Task Nature (hidden)
Task Nature
1 | Streamline/Improvements
2 | Regular reporting
3 | Upskilling
4 | Automations
5 | Onboarding
6 | Ad-hoc