## data
Task_ID | Assigner | Next Sprint? | Completed | Task Set Date | Completion Date | Deadline | Nature | Roadblock | Task_Description | tASK_PRIORITY | Hours | Task_workload FTE | Closing Comment (If Applicable)
1 | Brian | N | Y | 2021-06-07 | 2021-06-09 |  | Onboarding | None | get VPN access sorted | 4 | 0.5 | 0.064516
2 | Brian | N | Y | 2021-06-07 | 2021-06-09 |  | Onboarding | None | Read Teams documentation and familiarize with file locations | 4 | 2 | 0.25806
3 | Brian | N | Y | 2021-06-07 | 2021-06-09 |  | Onboarding | None | Setup SQL Task Tracker | 4 | 2 | 0.25806
4 | HR | N | Y | 2021-06-07 | 2021-07-30 |  | Onboarding |  | Get through Eloomi onboarding modules | 3 | 50 | 6.4516 | N/A
5 | Simon | N | Y | 2021-06-07 | 2021-07-21 |  | Streamline/Improvements | None | Streamlining Datasources and interrogate PowerBI accuratcy(Contracts tab) | 1 | 20 | 2.5806 | Happy with All except savings bar. New Task to rebuild Savings data source
6 | Simon | N | Y | 2021-06-07 | 2021-06-09 |  | Onboarding | None | Understand Savings report) | 3 | 6 | 0.77419
7 | Simon | N | Y | 2021-06-07 | 2021-06-09 |  | Onboarding | None | Reach to Will foley(IT) to get access to SAP | 4 | 1 | 0.12903
8 | Simon | N | Y | 2021-06-07 | 2021-06-09 |  | Onboarding | None | get Pbix file off Dan Craley | 4 | 1 | 0.12903
10 | Simon | N | Y | 2021-06-07 | 2021-06-09 |  | Onboarding | None | Familiarize myself with intranet procurement sharepoint | 4 | 1 | 0.12903
11 | Simon | N | Y | 2021-06-07 | 2021-06-09 |  | Ad-hoc | None | Troubleshooting global dashboard why data not putting through | 4 | 2 | 0.25806
14 | Brian | N | Y | 2021-06-08 | 2021-07-30 |  | Onboarding | None | competent with wednesday meeting schedule | 2 | 4 | 0.51613 | N/A
16 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Ad-hoc | None | update on when the KPI rport will be available | 2 | 0.5 | 0.064516
17 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Ad-hoc | None | Setup for team site with security control for sensitive client information | 4 | 1 | 0.12903
18 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Ad-hoc | None | Clarify requirement, SRM page report p.42 of instruction, are we suppose to build it, or maintain whats already in place and amend metrics? activity tracker SRM tab formula’s not working, needs conversation Nick to understand how its setup | 4 | 1 | 0.12903
19 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Onboarding | None | Learn to Navigate teams | 4 | 2 | 0.25806
20 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Onboarding | None | Read through 50 page instruction on how to run the pbix file and maintain datasources | 4 | 3 | 0.3871
21 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Onboarding | None | Setup sap hana account | 4 | 2 | 0.25806
22 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Ad-hoc | None | Conversation with Simon rolling 12 figures gone static, Need understanding of datasource | 4 | 1 | 0.12903
23 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Data | None | Input GNFR Procurement overview tab MAY’ spend and savings data | 4 | 1.5 | 0.19355
24 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Ad-hoc | None | 1 Vendor “MIDDLESOFT” missing in masterdata sheet, vendor code 23027. Troubleshoot to find where masterdata comes from | 4 | 0.5 | 0.064516
25 | Brian | N | Y | 2021-06-08 | 2021-06-10 |  | Ad-hoc | None | troubleshoot usual spend 260m, 199m logging for overall across all category of spend, data accuracy needs improvement | 4 | 2 | 0.25806
26 | Dan | N | Y | 2021-06-08 | 2021-06-10 |  | Onboarding | None | read GNFR Cleared Spend Report guide | 4 | 1 | 0.12903
27 | Nick | N | Y | 2021-06-08 | 2021-06-10 |  | Ad-hoc | None | Fix SRM middle donut chart not reflecting correct metrics, shouldn’t be over 100k | 3 | 1 | 0.12903
28 | Nick | N | Y | 2021-06-08 | 2021-06-10 |  | Discovery | None | Understand SRM data, refresh/rebuild top graphic to work again | 3 | 1 | 0.12903
30 | Nick | N | Y | 2021-06-08 | 2021-06-10 |  | Onboarding | None | Read Ryan handover guide | 4 | 2 | 0.25806
31 | Nick | N | Y | 2021-06-08 | 2021-06-10 |  | Discovery | None | learn/ ask rebecca case on how to maintaining mailbox | 4 | 2 | 0.25806
32 | Siobhan | N | Y | 2021-06-08 | 2021-07-05 |  | Improvement | None | Contract coverage report Region can be more pinpoint, currently reporting bysupplier location, ideally where its funded. | 4 | 4 | 0.51613 | Raw Spend collated into distince vendor number, (If further details wanted can expand heirachy
33 | Siobhan | N | Y | 2021-06-08 | 2021-06-10 |  | Quick Win | None | Put in double ribbon, breakdown on region as well as category of spend | 4 | 0.25 | 0.032258
34 | Siobhan | N | Y | 2021-06-08 | 2021-06-10 |  | Fix | None | Top ribbon on primary classification not toggling | 4 | 0.5 | 0.064516
35 | Dan | N | Y | 2021-06-09 | 2021-07-07 |  | discovery | None | Reverse Engineer whole kpi_live dashboard, map out datasources | 1 | 35 | 4.5161 | Task Obsolete, whole report rebuilt
36 | Dan | N | Y | 2021-06-09 | 2021-06-11 |  | System Access | None | docusign access for Ali | 4 | 0.25 | 0.032258
37 | Dan | N | Y | 2021-06-09 | 2021-06-11 |  | discovery | None | Reverse engineer contract coverage report, mapout datasources | 4 | 5 | 0.64516
38 | Perrin | N | Y | 2021-06-09 | 2021-06-11 |  | Ad-hoc admin | None | Group Buyer PowerPoint for Perrin | 4 | 0.5 | 0.064516
39 | Brian | N | Y | 2021-06-10 | 2021-06-12 |  | Ad-hoc admin | None | Quick Excel Analysis on Stores and management fees from HR | 4 | 0.5 | 0.064516
146 |  | N | Y | 2021-09-01 | 2021-09-03 |  | Data |  | load in august mentor data/saving
41 | Brian | N | Y | 2021-06-14 | 2021-06-16 |  | System Access | None | Lisa Baker docusign access | 4 | 0.25 | 0.032258
42 | Brian | N | Y | 2021-06-14 | 2021-06-16 |  | System Access | None | Winshuttle Access From Phil Humpries | 4 | 1 | 0.12903
43 | Brian | N | Y | 2021-06-14 | 2021-06-16 |  | System Access | None | Intranet edit Access From Kevin Hawkes | 4 | 1 | 0.12903
44 | Simon | N | Y | 2021-06-14 | 2021-07-08 |  | Ad-hoc admin | None | Update Intranet Procurement team Org Chart. | 4 | 4 | 0.51613 | N/A
45 | Brian | N | N | 2021-06-15 | Not applicable |  | admin | None | Monthly for all of my workstreams, map out steps on visio | 4 | 1 | 0.12903 | N/A
46 | Brian | N | Y | 2021-06-15 | 2021-06-17 |  | Discovery | None | SAP video not helpful with setup, look for support from IT | 4 | 2 | 0.25806
47 | Brian | N | N | 2021-06-15 | Not applicable |  | admin | None | Document Ongoing workstream and procedures | 4 | 0.5 | 0.064516 | N/A
48 | HR | N | Y | 2021-06-15 | 2021-06-17 |  | System Access | None | Paul Wilson Docusign Access | 4 | 0.25 | 0.032258
49 | Simon | N | Y | 2021-06-15 | 2021-06-17 |  | Onboarding | None | Quick excel sheet Datasheet manipulation for Perrin | 4 | 0.5 | 0.064516
51 | Simon | N | Y | 2021-06-15 | 2021-06-17 |  | discovery | None | Undergo SAP Training | 4 | 3 | 0.3871
52 | Simon | N | Y | 2021-06-15 | 2021-06-17 |  | Ad-hoc admin | None | Download SAP Tutorial video and reupload in centralized team space | 5 | 1 | 0.12903
53 | Brian | N | Y | 2021-06-18 | 2021-07-16 |  | discovery | None | Ask Dan for a list of Acronyms for SAP hana studio Classification tables | 1 | 0.5 | 0.064516 | N/A
54 | Brian | N | Y | 2021-06-18 | 2021-07-21 |  | discovery | None | Clarify maintanence task on handout guide, specifically for winshuttle workstream | 4 | 0.5 | 0.064516 | No one Knows, self discovery and handout guides took a while
55 | Perrin | N | N | 2021-06-18 | Not applicable |  | admin | None | Maintain daily reporting on SAP PO updates for Sally Ponting | 4 | 0.25 | 0.032258
57 | Brian | N | Y | 2021-06-21 | 2021-06-23 |  | discovery | None | Understand more about who owns global activity tracker. potential for process improvement | 3 | 0.25 | 0.032258
58 | Nick | N | Y | 2021-06-21 | 2021-06-22 |  | fix | None | kpi_live: Fix Data errors in SRM Tab | 3 | 3.5 | 0.45161 | N/A
59 | Simon | N | Y | 2021-06-21 | 2021-06-23 |  | admin | None | double check contract coverage report auto-refresh switched on 6pm tuesday | 1 | 0.5 | 0.064516 | Checked Dataflow autorefreshs
60 | Simon | N | Y | 2021-06-21 | 2021-06-23 |  | development | None | Contract Coverage report donut chart set colour change green-amber at 95% threshold | 4 | 0.5 | 0.064516
61 | Brian | N | Y | 2021-06-22 | 2021-06-24 |  | development | None | Amend Personal tracker report, add time consumption field of task, and task priority on dashboard | 5 | 0.5 | 0.064516 | Counted in hours, direct conversion to FTE (Full time day equivalents)
65 | Brian | N | N | 2021-06-22 | Not applicable |  | admin | None | Raise Question with Docusign Janet monthly on licensing and the quantity of of envs we have with deleting onboarding/offboarded colleages. | 3 | 1 | 0.12903 | Ongoing Maintanence, wont Close
66 | Brian | N | Y | 2021-06-22 | 2021-06-24 |  | admin | None | Ongoing reporting tasks have regular time blocked out on outlook Calender | 4 | 0.25 | 0.032258
67 | Brian | N | Y | 2021-06-22 | 2021-06-24 |  | discovery | None | Ask Ewan about End-to-End Windshuttle Process and document current failing Points | 4 | 2.5 | 0.32258
68 | Brian | N | Y | 2021-06-22 | 2021-06-24 |  | development | None | Personal Tracker--- create relative workload field, task nature and priority field | 4 | 4 | 0.51613
69 | HR | N | Y | 2021-06-22 | 2021-06-24 |  | System Access | None | Revoke Amy Marino Docusign | 4 | 0.25 | 0.032258
70 | Katy | N | Y | 2021-06-22 | 2021-06-24 |  | Ad-hoc admin | None | Supply Chain Cost to Serve PO Extract from SAP, for Katy +Perrin | 1 | 1 | 0.12903
71 | Simon | N | N | 2021-06-22 | Not applicable |  | admin | None | Thursday 1430 Docusign Check for pending access requests | 3 | 0.5 | 0.064516 | Ongoing Maintanence, wont Close
72 | Simon | N | N | 2021-06-22 | Not applicable |  | Ad-hoc admin | None | Mid week, EOW Procurement Mailbox Check | 4 | 0.5 | 0.064516 | Ongoing Maintanence, wont Close
73 | Simon | N | Y | 2021-06-22 | 2021-06-24 |  | System Access | None | Gain Acccess to Concur | 2 | 0.01 | 0.0012903
75 | Simon | N | Y | 2021-06-22 | 2021-07-21 |  | discovery | None | Draw up Windshuttle end-to-end responsibility and hyperlink to responsibility one-pager | 2 | 3.5 | 0.45161 | Scheduled in 2 hours with Anna baker to learn this
76 | Simon | N | Y | 2021-06-22 | 2021-06-24 |  | fix | None | Make changes to SEA Owner on Windshuttle | 4 | 1 | 0.12903
77 | Katy | N | Y | 2021-06-23 | 2021-06-25 |  | data | None | Export SAP Data for Royal Mail, Compare Blanket spend and try to find actual spend through invoice | 1 | 0.5 | 0.064516
78 | Perrin | N | Y | 2021-06-23 | 2021-06-25 |  | Ad-hoc admin | None | Winshuttle teams instruction need validation with CDS Phil Humphry, Kevin Hawk as it needs to go Live ASAP | 1 | 3 | 0.3871
79 | Perrin | N | Y | 2021-06-23 | 2021-06-25 |  | development | None | Contract Coverage report Change dropdown menu back to Click buttons, more user friendly | 1 | 0.5 | 0.064516
80 | Simon | N | Y | 2021-06-23 | 2021-06-25 |  | development | None | Contract Coverage report is showing No Contract required, but also showing up in expiring next 6months, set exclusion rule | 1 | 2 | 0.25806
81 | Simon | N | Y | 2021-06-23 | 2021-06-25 |  | development | None | Contract Coverage report Refresh report and set autorefresh to tuesday 6pm, Siobhan corporate entry NEEDS to come off | 1 | 2 | 0.25806
82 | Simon | N | N | 2021-06-23 | Not applicable |  | Ad-hoc admin | None | Weekly Teams Page Clean up | 3 | 0.5 | 0.064516 | N/A
83 | Siobhan | N | Y | 2021-06-23 | 2021-06-25 |  | data | None | 2 clients vendor number 22987,11441 shouldnt pop up at all in Siobhans report | 1 | 0.5 | 0.064516
84 | Siobhan | N | Y | 2021-06-23 | 2021-06-25 |  | data | None | Consolidate 2 clients both with vendor number 22847 | 1 | 0.5 | 0.064516
85 | Siobhan | N | Y | 2021-06-23 | 2021-06-25 |  | Ad-hoc admin | None | HR data extract Request to include 2019 data (One-off) | 4 | 0.5 | 0.064516
86 | Perrin | N | N | 2021-06-28 | Not applicable |  | Regular reporting | On Hold, re-org in process, not sure who's going to own process | Deliver Windshuttle training monthly, 3 sessions across the week | 1 | 4 | 0.51613 | N/A
87 | Perrin | N | N | 2021-06-28 | Not applicable |  | data | None | Maintain Global supplier and Buyer Distribution list weekly (Friday) for Sally Ponting | 3 | 0.25 | 0.032258 | N/A
88 | Perrin | N | N | 2021-06-28 | Not applicable |  | data | None | Maintain daily marketing marketing PO updates for Sally Ponting | 3 | 0.25 | 0.032258 | N/A
89 | Brian | N | Y | 2021-07-06 | 2021-07-07 |  | fix | None | Procurement Overview Page over80% contributing 20% chart needs fixin | 1 | 2 | 0.25806 | Fixed, Chart Conditional formating and % moving
90 | Brian | N | Y | 2021-07-07 | 2021-07-08 |  | fix | None | Help Katy With fixing Global activity tracker entries | 2 | 0.5 | 0.064516 | N/A
91 | Brian | N | Y | 2021-07-07 | 2021-08-09 |  | data | broke links, people used to where things are, don’t move around until more fresh blood | try and move static files (Global activity tracker, mentor FY2021 Spend to shared teams folders and off sharedrive.) | 3 | 0.5 | 0.064516 | N/A
93 | Rebecca | N | Y | 2021-06-28 | 2021-06-29 |  | data | None | 27769 needs to come off rebecca's pile | 2 | 0.2 | 0.025806 | N/A
94 | Siobhan | N | Y | 2021-06-28 | 2021-06-29 |  | data | None | 26793 needs to come off siobhans pile | 2 | 0.2 | 0.025806 | N/A
95 | Perrin | N | Y | 2021-06-28 | 2021-07-16 |  | data | Discussion to be had across team | Line by Line Wednesday show potentially just go high level metrics, 1once a month line by line deepdive | 2 | 5 | 0.64516 | Conclusion reached, go through weekly trend. And deepdive into number metrics monthly
96 | Brian | N | Y | 2021-07-08 | 2021-07-21 |  | Discovery |  | Learn how to check Payment terms (Get XK03 Access) | 2 | 2 | 0.25806 | Not suppose to have XK_03 Access. Forward enquiries to AP.
97 | Simon | N | Y | 2021-07-08 | 2021-07-13 |  | Discovery |  | Reach out to Anne Baker to do Windshuttle form raising run through | 1 | 1.5 | 0.19355 | Ad -hoc help with actually filing the form required.
98 | Siobhan | N | Y | 2021-07-08 |  |  | Ad-hoc admin |  | ad hoc PO request for Siobhan (Italian tax) | 1 | 0.5 | 0.064516 | N/A
99 | Simon | N | Y | 2021-07-08 | 2021-07-14 |  | Ad-hoc admin |  | upload windshuttle instructions from Simon to Purchase to Pay excellence centre, & Procurement team training | 1 | 0.2 | 0.025806 | N/A
100 | Simon | N | Y | 2021-07-08 | 2021-08-11 |  | data |  | Data Clean for Global Activity Tracker, Fix Validation Columns | 1 | 2 | 0.25806 | End up rebuilding it from scratch. Too messy initially anyway
101 | Simon | N | N | 2021-07-08 | Not applicable |  | data |  | Every Wednesday take snapshop of kpi live (Spend Under contract, no. of supplier under contract, YTD Average payment days vs LY, % of Supplier Spend over 80% | 1 | 0.5 | 0.064516
102 | Brian | N | Y | 2021-07-08 | 2021-08-09 |  | fix | Dataflows broke after takeover, manaully refreshing at the moment | Take over Dataflow on workspace, troubleshoot session with Dan scheduled to fix authentication credentials | 3 | 2 | 0.25806 | N/A
110 | Rebecca | N | Y | 2021-07-09 |  |  | data |  | Louide Contract not required | 1 | 0.1 | 0.012903 | N/A
104 | Brian | N | Y | 2021-07-09 | 2021-07-15 |  | Ad-hoc admin |  | draw up teams page structure visio | 2 | 2 | 0.25806 | N/A
105 | Brian | N | Y | 2021-07-13 |  |  | development | Awaiting final confirmation on what fields to keep on central view, then can go ahead and patch onto kpi live | Rebuild Global activity Tracker Offline | 1 | 20 | 2.5806 | N/A
|  |  | Y | 2021-07-13 | 2021-07-14 |  | Discovery |  | SRM page deepdive, what the metrics mean, how should we change them | 1 | 1 | 0.12903 | N/A
|  |  | Y | 2021-07-13 | 2021-07-14 |  | Ad-hoc admin |  | Add PowerBI App tab onto general teams Page | 1 | 0.5 | 0.064516 | N/A
107 | Brian | N | Y | 2021-07-13 | 2021-07-14 |  | data |  | Check with Ewan that Nick Hill's Ven003 is reassigned to Rebecca. No confirmation today | 1 | 0.5 | 0.064516 | N/A
108 | Simon | N | Y | 2021-07-14 | 2021-07-15 |  | Discovery |  | Consolidate excel sheet understanding received from Simon into Filing structure on Teams. | 2 | 2 | 0.25806 | N/A
109 | Phil | N | Y | 2021-07-14 | 2021-07-14 |  | data |  | Jade and Dr Peng mark off on contract not required List | 1 | 0.2 |  | N/A
111 | Brian | N | Y | 2021-07-14 | Not applicable |  | Ad-hoc admin |  | Consolidate global buyer supplier mailing list with existing live sheet from sally ponting | 1 | 0.5 | 0.064516 | N/A
112 | Brian | N | Y | 2021-07-14 | 2021-08-09 |  | fix | in Conversation with Dan on how to either rebuild, or use all of them throuh SAP connections | fix market dojo dataflow not working | 1 | 2 | 0.25806 | N/A
40 | Brian | N | N | 2021-06-14 |  |  | Discovery | Not Figured out Regular reporting pattern yet, org change | Data Producement Analtst Monthly Schedule on a timeline | 4 | 3 | 0.3871 | N/A
114 | Siobhan | N | Y | 2021-07-16 | 2021-07-20 |  | Ad-hoc admin |  | Fix New Supplier Pack hyperlink | 1 | 0.5 | 0.064516 | N/A
115 | Brian | Y | Y | 2021-07-16 | 2021-07-30 |  | development |  | Sprint Model for personal tracker | 2 | 0.5 | 0.064516 | N/A
114 | Siobhan | N | Y | 2021-07-23 | 2021-08-02 |  | fix | Contract refresh Issues on Market Dojo, Dataflow broke, credential issue.. | OMD contract renewed, infospring on contract not required, figure out why they arent coming off the list. | 2 | 1 | 0.12903 | N/A
115 | siobhan | N | N | 2021-07-26 | Not applicable |  | data | Contract refresh Issues on Market Dojo, not validating "contract not required list as refresh cant pull through yet" | monthly spend report for each category of spend | 2 | 0.5 | 0.064516
116 | Perrin | N | Y | 2021-07-26 | 2021-08-18 |  | data |  | change metrics from 100K limit to 50 K Limit | 1 | 2 | 0.25806 | Phil too busy Ewan amended and closed ticket
117 | Perrin | N | Y | 2021-07-26 | 2021-08-18 |  | data |  | GNFR vendor form on winshuttle needs amending, 100k to 50k | 2 | 0.25 | 0.032258 | Phil too busy Ewan amended and closed ticket
118 | Perrin | N | Y | 2021-07-26 | 2021-08-11 |  | Ad-hoc admin | List sent off to CDS, awaiting response | GNFR vendor form, refresh dropdowns, some names are too old | 3 | 0.25 | 0.032258 | N/A
119 | Brian | N | Y | 2021-07-26 |  |  | development | will break the report temporarily, should probably do out of hours | Change input method from marketDojo From dataflow to direct import | 3 | 1 | 0.12903 | N/A
120 | Perrin | N | Y | 2021-07-26 |  |  | Teaching | need contextual understanding on each and every category and dry runthroughs | Learn every winshuttle dropdown meeting and hold monthly global training | 1 | 2 | 0.25806 | N/A
113 | Brian | N | N | 2021-07-16 |  |  | Discovery |  | build a list of SAP hahna acronyms for databases | 3 | 6 | 0.77419 | N/A
122 | Simon | N | N | 2021-08-03 |  |  | Regular reporting |  | sending out regular reminders for monthly update on global actvity tracker End of Month | 1 | 0.1 | 0.012903
123 | Simon | N | Y | 2021-08-03 | 2021-08-13 |  | data |  | Amend colums on vendor master report | 2 | 0.1 | 0.012903 | N/A
124 | Simon | N | Y | 2021-08-03 |  |  | System Access |  | activate docusign account for Simon Jones | 2 | 0.15 |  | N/A
124 | Simon | N | N | 2021-08-03 |  |  | Regular reporting |  | monthly Savings refresh from global activity tracker to Savings Tracker | 1 | 0.2 | 0.025806
125 | Simon | N | Y | 2021-08-04 | 2021-08-05 |  | System Access | Siobhans out, no one else has super-admin, Raised with Account Lead, should be rsolved, need confirmation | get Simon elevated Market Dojo Access |  |  | 0 | N/A
126 | Simon | N | Y | 2021-08-04 | 2021-08-19 |  | Ad-hoc admin |  | get CDS to amend Winshuttle form | 1 | 1 | 0.12903 | N/A
127 | Katy | n | N | 2021-08-06 |  |  | Ad-hoc admin |  | Supplier roadmap report for Katy | 1 | 0.5 | 0.064516
128 | Simon | N | Y | 2021-08-10 | 2021-08-13 |  | fix |  | Global activity tracker VBA amendment, Auto generate unique ID | 1 | 0.5 | 0.064516 | N/A
129 | Simon | n | N | 2021-08-10 |  |  | development |  | Global Activity tracker increase in scope, include category divided roadmap | 1 | 7 | 0.90323
130 | Simon | N | Y | 2021-08-10 | 2021-08-13 |  | fix |  | Kpi Live, fix contract coverage donut, broke again after marketdojo api integrated | 1 | 1 | 0.12903 | Filters were limiting wrong metrics, chart seperated and fixed with individual parameters
131 | Simon | N | Y | 2021-08-10 | 2021-08-13 |  | data |  | kpi live pull in value column for contract gaps, and contract expiring in 6 months | 1 | 1.5 | 0.19355 | N/A
132 | Simon | N | Y | 2021-08-11 | 2021-08-13 |  | data |  | investigate why some of the marketdojo contracts have left | 1 | 2 | 0.25806 | BD on the marketdojo side messed up, nothing to do with my tracker
121 | Brian | N | N | 2021-08-02 |  |  | fix |  | fb1l dataflow not working, interrogate script in Ryans library and rebuild in power query | 2 | 3 | 0.3871 | N/A
| Siobhan | N | Y | 2021-08-13 | 2021-08-13 |  | Ad-hoc admin |  | Fix ACH Agreement form | 1 | 1 |  | N/A
128 | Hans | N | Y | 2021-08-16 | 2021-08-17 |  | System Access |  | Hans access to marketdojo, winshuttle, procurement mailbox, mailing list | 1 | 1.5 | 0.19355 | N/A
128 | Simon | N | Y | 2021-08-11 | 2021-08-22 |  | System Access |  | Call helpdesk to figure out why my Teams Sync isnt working… bring up global activity tracker example |  |  |  | N/A
127 | Simon | N | N | 2021-08-11 |  |  | Discovery | Support from Dan to familiarize myself with SQLhana | Write SQL Query in Hana to pull out monthly spend data per category | 1 | 6 | 0.77419 | N/A
129 | Simon | N | Y | 2021-08-23 | 2021-08-29 |  | development |  | Change on AT tracker, Modify Titles, Fix VBA script for insert line button | 2 | 0.5 | 0.064516 | N/A
130 | Simon | N | Y | 2021-08-23 | 2021-08-25 |  | Ad-hoc admin |  | freeze panes on AT tracker. | 2 | 1 | 0.12903 | N/A
| Simon | N | Y | 2021-08-24 | 2021-08-24 |  | handover |  | Handover extract for Siobhan |  |  |  | N/A
| Brian | N | Y | 2021-08-24 | 2021-08-24 |  | development |  | Replace Savings bar with new global activity tracker data |  |  |  | N/A
| Brian | N | Y | 2021-08-24 | 2021-08-25 |  | development |  | replace SRM tab with new global activity tracker data |  |  |  | N/A
133 | Simon | N | Y | 2021-08-25 | 2021-08-25 |  | Ad-hoc admin |  | re-assign katy's docusign envelopes to Hans and Simon |  |  |  | N/A
134 | Olivia | N | Y | 2021-08-25 | 2021-08-25 |  | data |  | Validate Imperial dade information |  |  |  | N/A
131 | Simon | N | Y | 2021-08-23 | 2021-08-29 |  | fix |  | get overview savings targets to filtering just on ITY savings |  |  | 0 | N/A
135 | Siobhan | N | Y | 2021-08-25 | 2021-09-02 |  | fix |  | Interrogate cateogry 3 fields on kpi misalignment |  |  | 0 | N/A
|  | N | Y | 2021-08-25 | 2021-08-25 |  | System Access |  | Siobhan contract envolope access for simon |  |  |  | N/A
136 | Simon | N | Y | 2021-08-25 | 2021-08-29 |  | data |  | interrogate top line metrics validation with Simon on the procuremet overview |  |  | 0 | N/A
138 |  | N | Y | 2021-08-27 |  |  | System Access | N | Ali access to marketdojo, winshuttle |  |  | 0 | N/A
139 | Simon | N | Y | 2021-08-27 | 2021-09-10 |  | data |  | central view tab comments data quality issue | 1 | 6 | 0.77419 | N/A
140 | Simon | N | N | 2021-08-27 |  |  | development |  | SRM tab % build new calculated metric | 2 | 1 | 0.12903 | N/A
141 |  | N | Y | 2021-08-27 | 2021-08-29 |  | fix |  | validate YTD supplier setup time with Simons offline output sheet |  |  | 0 | N/A
142 |  | n | Y | 2021-08-29 | 2021-08-29 |  | System Access |  | docusign access for rebecca, andrea |  |  |  | N/A
143 |  | n | Y | 2021-08-29 | 2021-09-02 |  | Ad-hoc admin |  | Move all recorded training material to teams, create training calender |  |  |  | N/A
142 | Simon | N | Y | 2021-09-13 | 2021-09-13 |  | Fix |  | Fault find on global activity tracker what loose links are causing error msg | 1 | 0.5 | 0.064516 | There were pathways pointing towards old excel files that were sitting on prem, These files have been moved but pathways remain. I have extracted data from old files into new tracker, but hyperlinks still active. Edited startup prompt to neglect errors
143 | Simon | N | y | 2021-09-13 | 2021-09-13 |  | data |  | Transfer contracts from Siobhan to Ali, Deactivate Siobhans acct | 1 | 0.5 | 0.064516 | N/A
144 | Myself | N | Y | 2021-09-17 | 2021-09-20 |  | data |  | Building category of spend heirachy and reclassify for cleaner data | 2 | 0.5 | 0.064516 | N/A
145 | Simon | N | Y | 2021-09-14 | 2021-09-14 |  | data |  | Pull through VDM data from PowerBI into SRM tab (ITY savings, and Rolling 12 ) | 2 | 0.25 |  | N/A
146 | Simon | N | Y | 2021-09-14 | 2021-09-16 |  | Ad-hoc admin |  | Winshuttle Portal Update, Remove Procurement site specific Buyer list, Streamline and point at finance's central buyer supplier matric | 1 | 0.5 | 0.064516 | N/A
147 | Simon | N | N |  |  |  | data |  | have the 2020 Data extracted from old tracker to add to current tracker to drive category breakdown of previos savings | 3 | 3 | 0.3871 | N/A
148 | Simon | N | Y | 2021-09-16 |  |  | data |  | SRM data clean (Line by Line Validation) | 1 | 2 | 0.25806 | N/A
148 | Simon | N | N | 2021-09-16 | 2021-09-16 |  | development |  | SRM metric change | 1 | 1 | 0.12903 | N/A
49 | Simon | n | Y | 2021-09-16 | 2021-09-16 |  | Ad-hoc admin |  | update intranet site | 3 |  | 0 | N/A
150 | Simon | n | n |  |  |  | Ad-hoc admin |  | ALC ven report cleanup | 2 | 0.25 | 0.032258 | N/A
151 | Simon | n | Y | 2021-09-24 | 2021-09-24 |  | development |  | Incorporate monthly winshuttle process time as a reporting metric to included into powerBI | 2 | 1 | 0.12903 | N/A
152 | Simon | n | Y | 2021-09-22 | 2021-09-23 |  | handover |  | Draw out Data structure for kpi live | 2 | 2 | 0.25806 | N/A
153 | Simon | n | N |  |  |  | handover |  | Rewrite Handover Guide | 1 | 5 | 0.64516 | N/A
154 | Simon | N | N | 2021-09-24 |  |  | data |  | monthly update on winshuttle report in powerBI | 2 | 0.5
154 | Simon | [5 empty] | Ad-hoc | Lewis has to get in touch with Marketdojo development team for change in their onlline portal | work with Lewis to add Primary category column in market dojo | 3 | 1 | 0.12903 | N/A
155 | Simon | N | N |  |  |  | Ad-hoc |  | Map out Items sitting under ecomerce, digital marketing on market dojo, re-assign after discussion with Ali and Simon and reach to Lewis to re-categorize on dojo end | 3 | 0.5 | 0.064516 | N/A
156 | Simon | N | y | 2021-09-24 | 2021-09-24 |  | System Access |  | give Simon access to all categories on Dojo | 1 | 0.25 | 0.032258 | N/A
157 | Simon | Y | N | 2021-10-04 |  | 2021-10-07 | System Access |  | Give Simon Super Admin Permission to winshuttle , and market Dojo | 1 | 0.25 | 0.032258 | N/A
158 | Simon | Y | N | 2021-10-04 |  | 2021-10-07 | handover |  | Handover existing data reltaed tasks to Dan C | 1 | 0.5 | 0.064516 | N/A
159 | Simon | Y | N | 2021-10-04 |  | 2021-10-07 | handover |  | Handover existing Team support Tasks to Simon | 1 | 2 | 0.25806 | N/A
160 | Brian | N | N | 2021-10-05 |  | 2021-10-25 | Future Task |  | Dummy Task 1 | 1 | 4 | 0.51613 | N/A
161 | Brian | N | N | 2021-10-05 |  | 2021-10-28 | Future Task |  | Dummy Task 2 | 2 | 3 | 0.3871 | N/A
162 | Brian | N | N | 2021-10-05 |  | 2021-11-11 | Future Task |  | Dummy Task 3 | 3 | 2 | 0.25806 | N/A
163 | Brian | N | N | 2021-10-05 |  | 2021-11-15 | Future Task |  | Dummy Task 4 | 4 | 5 | 0.64516 | N/A
164 | Brian | N | N | 2021-10-05 |  | 2021-12-15 | Future Task |  | Dummy Task 5 | 4 | 1 | 0.12903 | N/A
165 | Brian | N | N | 2021-10-05 |  | 2021-12-01 | Future Task |  | Dummy Task 6 | 3 | 3 | 0.3871 | N/A
166 | Brian | N | N | 10/10.21 |  | 2021-12-05 | Future Task |  | Dummy Task 7 | 2 | 6 | 0.77419 | N/A
167 | Brian | N | N | 10/10.21 |  | 2022-12-02 | Future Task |  | Dummy Task 8 | 1 | 2 | 0.25806 | N/A
168 | Brian | N | N | 10/10.21 |  | 2022-12-15 | Future Task |  | Dummy Task 9 | 2 | 0.5 | 0.064516 | N/A
169 | Brian | N | N | 2021-11-17 |  | 2022-01-24 | Future Task |  | Dummy Task 10 | 3 | 2 | 0.25806 | N/A
170 | Brian | N | N | 2021-11-17 |  | 2022-01-01 | Future Task |  | Dummy Task 11 | 4 | 0.6 | 0.077419 | N/A

## Task Nature
Task Category | Category Description
Streamline/Improvements
Regular reporting
Upskilling
Automations
Onboarding
Ad-hoc